## Sheet1
Department | Description
Engineering Design | Add, Delete and Modify ILD, MOC, Terminals and Drawing or need to request and specify an element to be purchased.
Engineering Interface | Needs communication and co-operation with other contractors packages if we will have a loop crossing different contractors areas.
QC Department | Pending inspection.
Construction Department | Pending or wrong Field job.
Procurement Division | Needs to purchase an element which been approved by engineering.
Material Division | Missing an element in the warehouse.
Logistics Division | Delay in delivery for a purchased element.
Subcontractor Department | We need to assign a job for a subcontractor or a job in the field needs to have change order in the contracting.
Handover Department | Handover needs to apply field engineering instruction which denying QC for making the inspection due to data conflicting.
Project Director | An order has been given by Project Director holding some tasks to be done like an instruction to not call vendor in the current time to come or removing the generator from unit to another.
Client | Primary Task for the loop needs to be done by another contractor so the responsible is the client in front of us like we need the main control room in order to shoot the loop and this control room belongs to another contractor and it has been delayed in handed-over to us.
Human Resources Department | Everything is ready for the vendor but HR delaying the paperwork for the vendor visiting.