## Slide 1: Loop Workflow

## Slide 2: Agenda
Meeting Goal.
Loop Folder workflow.
Work Front.
Loop Process Digitalization.
Personas.
Case Scenario.

## Slide 3: Presentation goal
Establish a commitment workflow process and dedicated key positions.

## Slide 4: Loop Workflow

## Slide 5: Loop workflow - Overview
Pre-Comm
QC
QC Released
Folder Ready
Submit to Pre-Comm
Loop Done
Final Approval
QC Released: TR QC has verified and released all RFI required for one loop folder.
Folder Printed: ILD, Required RFI to be released for items related to the loop as per TR QC, P&ID and index sheet are printed and dossier in a folder.
Submit to QC: Folder handed over from Support Team to QC.
Folder Ready: Index sheet has been signed.
Submit to Support Team: Folder handed over to Support Team.
Submit to Pre-comm: Folder handed over to Pre-Comm Team.
Loop Done: Loop successfully performed.
Final Approval: Client Approved the folder, folder to be archived and responsibility goes to client.
Release
Folding
Perform
Folder Printed
QC
Submit to QC
Submit to Support Team
Auto
Auto
Auto
Auto

## Slide 6: Loop workflow - Detailed
Construction (Subcontractor)
Client/Mangt
Pre-Comm
QC Coordinator
Raise RFI
Print Folder
Construction Phase
Index Signed
Submit
Done
Final Approval
1
2
Released
Pre-Comm Phase
Engineering
Issued for cons./Red Line
Issued ILD
QC
QC Coordinator

## Slide 7: Work Front

## Slide 8: Loop Performed work front
Pre-Comm
QC Coordinator
Create priority for the loop folder as per Subsystem handover dates
Change
Inform
Released
Engineering
Planning
Loops System
Subcontractor
Construction
Report missing ILD

## Slide 9: Blockage Control

## Slide 10: Blockage management
Blockage Control and Notification Center
QC Coordinator
Engineering
Subcontractor
Construction
Register an Issue
Blockage management allow participant to register any constraint for the loop with integration with Notification center, so it is automatically notifying the responsible with the issue. And gives transparency to all why this loop is not performed.
Not only tracking but also gives the team a lesson learn for upcoming same loop in a different area to avoid the same blockage in advanced.
Folding
Release
Perform
Notify by Mail

## Slide 11: Personas

## Slide 12
Loop workflow Key person
  Folder Printed: QC.
  Folder Released: TR QC Team.
  Folder Ready: QC Coordinator.
  Loop Done: Pre commissioning team.
  Final Approved: QC Coordinator.

## Slide 13: Loop War Room

## Slide 14
Loop War Room
  It is an event kicks off the Loop performed. The purpose of War Room is to define what can be performed in the next week and how that work will be achieved.
  War Room is done in collaboration with the whole Key Persons.
  How is it done?
  During the War Room meeting, the Pre commissioning Owner describes the highest priority Loops to be performed. After pending items related to those loops are defined using (EICA Loop Map).
  Then, War Room works in one of two general ways: by considering a team's historical velocity or by considering a team's capacity. Also, Blockages and constraint is to be discussed if it has not been resolved for more than 2 weeks.
Loops Backlog
Priority Order
Select Pending Items
Remove Site conditions
Released
Construction Workfront
New Blockage

## Slide 15: Loop Process Digitalization

## Slide 16
Goal: Perform successfully loop checks fast and smooth.
Loop workflow digitalization
Mission: Collaboration over Negotiation.
Features:
  Single source of truth for all required information.
  Register Loop workflow steps.
  Blockage management system.
  Notification Center.
  QR code and cloudification.
  Easy Workfront.
  Integration with Production Control App.

## Slide 17: Thank you!